## Test Results Summary
CARRIER INTEGRATION TESTING - PHASE 1 RESULTS
Test ID | Carrier Name | Endpoint | Test Date | Status | Response Time (seconds) | Error Details | Notes
TC-001 | Carrier A | country-info | 2025-11-23 | Pass | 1.2 | - | Successfully returned country list
TC-002 | Carrier B | calculator | 2025-11-23 | Pass | 0.8 | - | Successfully calculated 100+250=350
TC-003 | Carrier C | number-convert | 2025-11-23 | Fail | - | ECONNRESET | API unavailable - see Jira KAN-1
TC-004 | Carrier C (alt) | country-currency | 2025-11-24 | Pass | 1.5 | - | Using as Carrier C replacement
Total APIs Tested: | 4
Tests Executed: | 4
Pass Rate:
Date Range: | Nov 23, 2025, - Nov 24, 2025

## API Performance
Carrier | Total Tests | Passed | Failed | Success Rate (%) | Avg Response Time (seconds)
Carrier A | 1 | 1 | 0 | 100% | 1.2
Carrier B | 1 | 1 | 0 | 100% | 0.8
Carrier C | 2 | 1 | 1 | 50% | 1.5
Total | 4 | 3 | 1 | 75% | 1.1667
Key Findings:
✅ Carrier B has fastest response time (0.8s)
✅ All active carriers meet <3s requirement
⚠️ Carrier C primary endpoint unavailable (documented in KAN-1)
✅ Alternative Carrier C endpoint performing well 📊 Overall system readiness: 75%
Recommendations:
Monitor Carrier C primary endpoint for restoration
Establish SLA with carriers for uptime requirements
Implement automated health checks
Add 5 additional test cases (see TC-005 through TC-009)

## Test Cases
Test Case ID | Test Description | Carrier | Input Data | Expected Result | Actual Result | Status | Priority
TC-001 | Retrieve country name by ISO code | Carrier A | sCountryISOCode: "US" | Returns "United States" | Returned "United States" | PASS | High
TC-002 | Calculate premium (base + addon) | Carrier B | intA: 100, intB: 250 | Returns 350 | Returned 350 | PASS | High
TC-003 | Convert number to words | Carrier C | ubiNum: 1500 | Returns "one thousand five hundred" | ECONNRESET error | FAIL | Medium
TC-004 | Retrieve currency by country | Carrier C | sCountryISOCode: "US" | Returns "USD" | Returned "USD" | PASS | High
TC-005 | Handle invalid country code | Carrier A | sCountryISOCode: "ZZ" | Returns error or empty | (Not tested yet) | PENDING | Medium
TC-006 | Test API timeout handling | All | Delayed response | System excludes carrier after 5s | (Not tested yet) | PENDING | High
TC-007 | Validate required fields | All | Missing required field | API returns 400 error | (Not tested yet) | PENDING | High
TC-008
TC-009
TC-010